## INDEX
2022 BLUEPRINT REVISION
OLD VERSION OF BLUEPRINT |  | SEND COMMENTS TO
MIKE WEISBERG
mweisb3808@gmail.com
BLUEPRINT TO END HOMELESSNESS
DRAFT REVISION
JUNE 2022
BLUEPRINT DOCUMENTS 2017 LINKS BELOW
BLUEPRINT TO END HOMELESSNESS
2017 VERSION
● LEADERSHIP SECTION, DRAFT 2022
● COORDINATED ENTRY SYSTEM, DRAFT 2022
● HOUSING, DRAFT 2022
● SERVICE DELIVERY, DRAFT 2022
● PUBLIC INFORMATION, DRAFT 2022
● PREVENTION, DRAFT 2022
BLUEPRINT EXPECTED OUTCOMES
2017 VERSION
RECOMMENDED BLUEPRINT REVISIONS
2022
THE REVISION INCLUDES SIX (6)
LINKS TO THE SECTIONS BELOW:
CONTINUUM OF CARE
GLOSSARY OF TERMS
CLICK LINK TO GLOSSARY

## GOAL 1 LEADERSHIP
OBJECTIVE 1: Strengthen Leadership to End Homelessness - To strengthen the Capital Area Coalition on Homelessness's leadership and organizational structure to implement a coordinated plan utilizing the Housing First Model to end homelessness.
Strategy 1.1) Improve CACH Governing Structure: Revisit the CACH's coordinating and standing committee structure and membership to effectively function as a Local Lead Agency and carry out the updated Blueprint Plan to prevent and end homelessness in Dauphin County
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.1a) Re-work the current Planning and Resource Development Committee into committees focused on planning, Blueprint implementation and on system-wide resource development. | Coordinating Committee | Completed | Planning & Resource Development Committee reorganized under Bylaw revision 2020 | Completed: Planning & Resource Development Committee's role clarified in revised Bylaws in accordance with Action Step: Strategy 1.1a
1.1b) Clarify the purpose and structure of all other Standing Committees and adjust bylaws as needed. | Coordinating Committee and Planning and Resource Development Committee | Completed | 10/13/17. Planning and Resource Deevelopment Committee revised existing committees, Bylaws, & made Recommendations to Coordinating Committee. Planning & Resource Development Committee reorganized with Standing Committee incorporated in the planning process under revised Bylaws 2020. | Completed: Planning & Resource Development Committee's role clarified in revised Bylaws in accordance with Action Step: Strategy 1.1a
Strategy 1.2) Increase CACH's member participation in collaborating, planning, and implementing the Blueprint to improve the capacity, cost efficiency and effectiveness of the homeless services system.
Action Step Description | Completed+B5:C5 | Target Date | Measurable Outcome(s) | Cumulative Progress
1.2a) Develop a recruitment strategy for involving providers and key leaders in the CACH leadership structure, including an effort to solicit broader landlord involvement in the coalition. | Planning and Resource Development Committee |  |  | The Capital Area Property Owners Association participates actively on the Housing Committee. The Housing Committee has also recruited private landlords for participation on the committee and in the planning process.
1.2b) Develop a format where agency executives/ program decision makers of homeless services providers can discuss system issues face to face on at least a semi-annual basis. | Planning & Resource Development Committee |  | Development of a CACH member agencies' Executive/Program Directors Work Group for the purposes of systemic planning and coordination. | Planning & Resource Development Committee will schedule first meeting in June/July 2022 in conjunction with the revision of the Blueprint revision. A schedule of future meetings and structure will be completed.
1.2c) Create an official communication tool to dispense important system information to all involved providers and members. | Public Education & information |  |  | Information distributed via member list serve. Important documents posted on the CACH web page
1.2d) Conduct regular meetings of all service providers to promote system coordination and networking. | Service Delivery |  |  | General membership meetings held quarterly
1.2e) Continue to build and maintain relationships with leaders in faith based community and grassroots organizations to partner efforts to provide housing and supportive services to homeless households. | Faith Based Initiatives |  |  | Evaluate the recommendation of combining the Public Information & Education and Faith Based Initiatives Committees. Review partnering with existing community initiatives/organizations that mobilize the community in social action initiatives.
Strategy 1.3) Provide training in the components of the HEARTH Act (Homeless Emergency Assistance and Rapid Transition to Housing Act) and the Housing First Model.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.3a) Create a resource which summarizes HUD and HEARTH Act objectives and priorities with definitions of terminology used within the homeless services system. | Public Education and Information Committee
1.3b) Schedule and conduct at least biannual training sessions using different venues/formats (web-based/seminars) regarding the Hearth Act and the Housing First Model | Service Delivery and Public Education and Information Committees |  |  | Service providers provide in-service on a ongoing basis. Training in Housing First and Domestic Violence are held annually.
Strategy 1.4) Incorporate the Point in Time, HMIS data, and System Performance Measures in the process of prioritizing service needs and to guide decisions regarding the allocation/reallocation of funding of the HUD Continuum of Care Program's Applications/Renewals.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.4a) Annually review and update/revise Continuum of Care (CoC) "Written Standards" on housing prioritization and housing outcomes based on current year and historic PIT and HMIS annual totals reports. | Planning and Resource Development Committee and CACH Board
1.4b) Utilize the Point in Time (PIT), HMIS data, Annual Performance Measures, and System Performance Measures to identify priority needs and make recommendations for the utilization of resources and funding for the Continuum of Care Application and other funding programs such as the HOME Program. | Planning and Resource Development and Standing Committees | Annually | Planning & Resource Development Committee conducts an analysis and submits recommendations to the CACH Board annually for program priorities for funding | Planning and Resource Development Committee conducted a review of the data in September 2021 and submitted priority program ranking to the CACH Board for Continuum of Care and HOME Application.
1.4c) Create an outline of HUD and HEARTH Act goals and priorities along with local priorities for homeless housing and services. | Planning and Resource Development Committee
1.4d) Develop a scoring matrix for the Continuum of Care Application ranking process incorporating priorities identified in the analysis of HMIS, PIT and System Performance Measures. | Review Team | Completed |  | Completed 9/2021: Continuum of Care Application Ranking Tool revised with data elements included.
1.4e) Incorporate/ update the scoring matrix into current CoC program ranking sheet. | Review Team | Completed | Revision of the COC application that includes program performance measures such as the Annual Performance Report (AHAR)
Strategy 1.5) Develop a multi-year, project-based comprehensive Resource Development Plan to engage local philanthropies and other funding sources in addressing homelessness as a priority
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.5a) Create a Resource Development Committee of providers, community leaders, philanthropies, public officials and foundations to assist in the development of a strategic plan to generate funding for priority Housing First services for homeless persons/families. | Planning and Resource Development | 2023 | Resource Development Committee conducts first meeting to develop a strategic plan to generate funding for Housing First Initiatives. | Harrisburg Housing Authority has initiated a working group with CACH's housing developers. HHA will provide support in capital generation and property management for new housing projects. The CACH Housing Committee is collaborating with the City and County for the development of five housing projects by Thrive, Brethren Housing, Veteran's Outreach and Fair Housing . CACH has also partnered with the Dauphin County Housing Authority for expansion of Housing Choice Vouchers opportunities and TriCounty Housing Development Corp for the Hummel Street Project.
Strategy 1.6) Ensure that the Housing First Model is promoted and infused in all possible services and programs through CACH’s Standing Committees
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.6a) Utilize membership meetings and training sessions to present information regarding the Housing First Model and best practices. | Public Education & Information |  | A training session regarding the Housing First Model will be conducted | Housing Committee provides reports at General Membership Meetings regarding the development of Housing First projects.
1.6b) Provide technical assistance and consultation to service providers developing permanent housing, Rapid Rehousing, or otherwise adapting programs to a Housing First Model. | Housing Committee | ONGOING | Technical assistance will be provided by the Housing Committee to promote the Housing First Model | The Housing Committee Meetings are used to educate and inform providers regarding the Model. Technical assistance has been provided to agencies to assist in the development of Housing First programs. Five development projects the are based upon the Housing First Model have been submitted for funding for Home-ARP.
Strategy 1.7) Solidify and expand the Drop-In Center as central point for accessing supportive services for unsheltered homeless persons through technical assistance and consultation.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.7a) Form a committee to provide consultation and assist the current Drop In Center in obtaining additional funding and resolving impediments to formalizing a long-term operational model. | Coordinating Committee | COMPLETED | Drop In Center established at Downtown Daily Bread. Shalom House has also established a walk in center. | Completed
1.7b) Assist in developing partnerships with supportive service providers for participation and provision of services at the Center. | Service Delivery, Prevention | COMPLETED | Drop In Center established at Downtown Daily Bread. Shalom House has also established a Walk in Center. | Completed
Strategy 1.8) Assure the completion of an Emergency Response Plan for natural disaster/ extreme weather for the homeless services system.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.8a) Partner with community Emergency Management Agencies, the Red Cross and other public safety officials and representatives from the Continuum of Care and its service providers to develop an emergency response for unsheltered persons/ families. | Service Delivery |  | Model and protocol developed for response to disasters | CACH developed process for responding specifically to the COVID pandemic. Procedures need to be formalized as a model for medical and non medical disasters. Identification of primary responsible lead agency needs to be included in a formalized procedural model.
1.8b) Prepare an Emergency Response Protocol for service providers and the outreach community to assist the Emergency Management Agency to assist homeless persons. | Service Delivery |  | Model and protocol developed for response to disasters | Formalize protocol used for COVID response for all forms of disasters. Identification of primary responsible entity for leadership role
1.8c) Identify an agency/entity to be the primary coordinator to communicate and manage the Continuum of Care Response. | Service Delivery |  | Model and protocol developed for response to disasters | Harrisburg Redevelopment Authority provided leadership during the COVID Pandemic. Identification of primary responsible lead agency needs too be included in formalized procedural model.
1.8d) Educate the Continuum of Care service providers and faith based organizations to the Emergency Response Protocol and procedures. | Service Delivery |  | Model and protocol developed for response to disasters
1.8e) Publish the Emergency Response Procedures on the CACH website. | Public Education & information |  | Model and protocol developed for response to disasters
Strategy 1.9) Partner with providers and statewide advocacy groups to advocate for effective polices and funding to support the goal of ending homelessness.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.9a) Participate as members in statewide and national housing and homeless coalitions dedicated to ending homelessness and developing safe and affordable permanent housing. |  |  |  | CACH members attend and participate in PA Housing Alliance and the National Low Income Housing Coalition programs and trainings. Members review training material, research and literature from advocacy groups such as the National Alliance to End Homelessness, Enterprise Foundation and Local Housing Solutions webpages.
1.9b) Participate in organizations and/or advocacy initiatives that promote services and benefits that are needed by homeless persons/families. | Public Education and Information Committee
1.9c) Comment and submit information for inclusion in the County and City Planning process and documents that will describe the needs for services for homeless persons/ families. | Standing Committees |  |  | Data is submitted when requested from local government entities.
1.9d) Assist in the development a Regional Housing Coalition that will address homeless services on a regional level. | Housing Committee |  | Standing Committees
1.9e) Work with key stakeholder groups to make progress toward recognizing the long-term effects on substance abuse and dependency as a disabling condition. | Housing Committee
Strategy 1.10) Maintain adequate staff to fulfill the administrative responsibilities of the Continuum of Care
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.10a) Evaluate the adequacy of current staff levels and potential need for additional staff to assist in the administration and implementation of CACH's responsibilities as the Continuum of Care Lead Agency. | CACH Board of Directors
1.10b.) Review the adequacy and sustainability of funding for the Continuum oof Care's administrative activities and develop a strategy if resources are insufficient. | CACH Board of Directors
Strategy 1.11) Maximize the utilization of funding resources for the Continuum of Care service delivery
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.11a) Monitor the utilization of Continuum of Care funding resources by conducting quarterly reviews of the grantees utilization of funds. | CACH Board of Directors |  | Design a procedure for the quarterly review of COC grants performance and utilization of funding
1.11b.) Conduct a review process for identifying underperforming agencies and assist in development of action plans to obtain full utilization of funding. | CACH Board of Directors |  | Design a procedure for the quarterly review of COC grants performance and utilization of funding. Meet with underperforming agencies to develop Action Plans and future monitoring
1.11c) Conduct an annual review to determine if funding resources are directed to the highest priorities based upon need of homeless households. Reallocate funding, if necessary, to redirect funding to the highest priorities/needs based upon an analysis of data elements | CACH Board of Directors |  | Design the Continuum of Care Application Review process to include a process for identifying priorities and allocating funding accordingly. | Policy established designating the Planning & Resource Development Committee as the entity responsible for identifying target populations and priority service needs. Review Team is responsible for evaluating Continuum of Care Applications and the performance of grantees and recommending programs that will address the priorities and serve target populations .
Strategy 1.12) Engage the community and local officials to ensure unsheltered homeless households have access to services that meet their health and hygiene needs.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.12a Ensure unsheltered households have access to services needed for basic hygiene such as showers and bathroom facilities. | Service Delivery, Planning & Resource Development, Public Information and Education |  |  | Plans are in progress for the development of Showers on Second (SOS) at the Shipoke Firehouse for shower facilities and personal storage. Currently exploring providing porta johns in the City for homeless persons.
1.12b. Establish communication with community organizations/neighborhood associations to provide information and seek their support in providing services/programs that fulfill health and hygiene needs of unsheltered persons. | Service Delivery, Planning & Resource Development, Public Information and Education
1.12c. Develop public informational material for release to the news media and social media to garner support for CACH's health and hygiene service components | Public Information and Education
Strategy 1.13) Redesign the committee structure to facilitate the an effective system to engage and mobilize the community to support CACH's programs and services
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.13a. Revise the current committee structure to facilitate promoting CACH's mission and engaging and mobilizing the community. Combine the Faith Based Initiatives and Public Education Committees with new strategies and objectives.
1.13b. Amend the Bylaws to facilitate the change in Committee structure.
Strategy 1.14) Develop a data quality review policy and process to insure the reliability and accuracy of HMIS data for use in the system performance evaluation and program planning.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.14a Develop policies and procedures that include Written Standards for data quality and a monitoring process. | Board of Directors
Strategy 1.15) Evaluate the need for expanding the shelter program for Victims of domestic Violence
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
1.15a Convene a task force to review the need for expansion of capacity and the feasibility of expanding services. | Planning and Resource Development Committee
RETURN TO INDEX

## GOAL 2 COORDINATED ENTRY (2)
OBJECTIVE 2: Coordinated Entry System (CES) - Monitor and evaluate the CES to document gaps in services, successes of programs, services and approaches and track progress toward meeting the goals of the CoC to make homelessness rare, brief, and non-recurring. |  |  |  |  | RETURN TO INDEX
Strategy 2.1) Develop a system to monitor and evaluate the Coordinated Entry System (CES) to document gaps in services, successes of programs, services and approaches, and to improve the CES within the CoC.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
2.1a) Establish baseline performance measurements for length of time from Screening to Placement on the CES prioritization list. | CES Committee
2.1b) Establish annual performance goals to improve the CES process. | CES Committee
2.1c) Establish a mechanism for measuring implementation and results such as regular reports on goals and outcomes for Coordinated Outreach to CACH. | CES Committee
2.1d) The Coordinated Entry Manager and a representative from CACH will meet with each participating program on an annual basis to monitor compliance with the CES Policies & Procedures, to ensure that improvement of the CES processes are identified. | CES Committee
2.1e) The Coordinated Entry Manager will regularly monitor the CES Prioritization List for accuracy of placement, priorities, and ease of use. | CES Committee
2.1f) The CES Access Sites and Participating Agencies will solicit feedback regarding the quality and effectiveness of the CES experience from paticipants who have utilitzed the system during their homeless experience. | CES Committee; Participating agencies
Strategy 2.2) Engage with CoC and non-CoC service providers to participate in the CES and referral process.
2.2a) Actively solicit non-CoC providers to engage and participate in the CES. | CES Committee
2.2b) Develop communication channels and partnerships with non-COC providers, especially faith-based groups, to both coordinate services and track outcomes. | CES Committee
2.2c) Engage all CoC and non-CoC providers to provide a representative on the CES committee. | CES Committee
2.2d) Provide annual CES Informational trainings to community entities and service providers to better connect individuals and families experiencing homelessness. | CES Committee
Strategy 2.3) Utilize the HMIS System to gather data outcomes from the CES starting at first contact until household is housed.
2.3a) Determine the data outcomes that the CoC needs for annual performance reviews, evaluation of the CES System and gaps in service. | CoC Board; PRD Committee
2.3b) Implement data reports that can be obtained within the HMIS system that can accurately and consistently produce the data necessary for continued improvement of the CES. | HRA Staff; CES committee
2.3c) Incorporate a mechanism for measuring prevention efforts in the community within the CES utilizing the HMIS system. | CES Committee
Strategy 2.4) Actively market and implement outreach efforts in the CoC community to ensure that all people within the CoC in need of homeless services will have fair and equal access to the CES.
2.4a) Broaden the marketing efforts of the CES to the community to ensure that all community stakeholders are aware of how to connect households experiencing homelessness to homeless and housing services. | CES Committee; PIE
2.4b) Ensure that all participating agencies/programs post or otherwise make publicly available a notice that describes the CES. | CES Committee
2.4c) Develop a training video on the CES that will be available on the CACH website for direct service staff and community stakeholders. | CES Committee; PIE
2.4d) Design index cards that provide basic CES access information to distribute to the community, emergency shelters, street outreach teams, etc. | CES Committee; PIE
2.4e) Explore ways to provide electronic access to the pre-screening form for individuals and families experiencing homelessness to provide fair and equal access to the CES. | CES Committee; HRA
2.4f) Develop access to CES after 4:00 pm | CES Committee

## GOAL 3 HOUSING
OBJECTIVE 3: Increase, and Preserve Existing, Affordable Housing – Utilizing a Housing First Model, provide a full range of safe and affordable permanent housing options for meet the needs of families and individuals experiencing or at risk of homelessness. |  |  |  |  | RETURN TO INDEX
Strategy 3.1) Explore the feasibility of specialized housing types for homeless and very-low-income families, such as Single Room Occupancy (SRO) and Shared Housing.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.1a) Meet and consult with stakeholders to expand existing and/or develop new affordable Single Room Occupancy(SRO) & Shared Housing units. | Housing Committee |  | Expand available opportunities
Housing Committee
3.1b) Explore the provision of supportive services for tenants of the potential new Single Room Occupancy& Shared Housing units with local service providers to ensure their successful retention of permanent housing. | Housing and Services Delivery Committees |  | Increase the percentage of persons maintaining housing and not returning to homelessness
3. 1c) Review Best Practices Model to explore the viability of creating a program of Shared Housing. | Housing Committee |  | Identify best practice Model for the development of future housing development | Identify best practices. Committee members attended Shared Housing Institute Conferences. Have contacted and reviewed Pad Split shared housing models. SHPD will review shared housing initiatives best practices in PA and report to committee
3.1d) Create a matching list or system whereby homeless participants willing to share housing can readily connect and apply for available housing. | Housing, and Service Delivery Committees |  |  | Deferred until completion of 3.1c
3.1e ) Develop a network of landlords with single family units who will rent to roommates following applicable city/county codes limits for unassociated members on a lease. |  |  |  | Action needed to amend City of Harrisburg Ordinances. See 3.1f
3.1f) Advocate for the revision of existing ordinances limited residency per home (housing unit) to 2 unrelated persons maximum. | Housing Committee, George Payne, HRA & Jacob Bowen, City of Harrisburg |  |  | Recommended ordinances revisions submitted to the City of Harrisburg that would allow development of shared housing
Strategy 3.2) Finalize the implementation of the new procedures to verify the Homeless Waiting List Preference for Public Housing and the Housing Choice Section 8 Vouchers for homeless persons for the Harrisburg Housing Authority and Housing Authority of the County of Dauphin
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.2a) Finalize the approval and implementation of the Homeless Preference in both Public Housing Authorities’ (PHA) operating plan. | Housing | 2021-01-22 | Public Housing Authorities have homeless preferences and use HMIS for verification of status | Both Housing Authorities are using HMIS as verification for homeless criteria/status for eligibility acceptance to HCV and PH Programs
3.2b) Finalize a system to verify a persons’ homeless status to meet the PHAs’ preference requirements using the HMIS system. | Housing Committee, Harrisburg Redevelopment Authority Staff | 2021-01-22 | PHAs use HMIS for verification | Both Housing Authorities are using HMIS as verification for homeless criteria/status for eligibility acceptance to HCV and PH Programs
3.2c) Educate service providers about the preference and the Homeless verification procedure required by the PHAs to apply the Homeless Preference for eligible homeless persons/families. | Housing Committee and Service Delivery |  | Persons entering CACH's system will have their contact information updated if they are on a PHA Waiting List | Need to develop a process for identifying persons who have applied and are on a PHA Waiting Lists and initiating an updating of their contact information. Include a question in HMIS application regarding status of PHA waiting list status.
3.2d) Review options with community service providers for the provision of supportive services for participants receiving the preference to ensure their successful housing retention. | Housing Committee and Service Delivery |  |  | Explore developing low level case management/monitoring for persons securing permanent housing that do not have mandatory services provisions. Explore developing follow-up monitoring by partnering with housing programs that have service coordinators
3.2e) Encourage participants accessing/receiving public housing assistance through the PHAs Homeless Preference to utilize renter’s consumer education programs. | Housing and Service Delivery Committees |  | Majority of households obtaining PH through PHA subsidy programs will have completed a PREP course | Review how to increase number of persons eligible for housing to enroll in PREP Programs
3.2f) Monitor the preference implementation and revise as needed. | Housing Committee |  | Has will utilize the HMIS System to verify a households’ “homeless status as defined by HUD | HRA will instruct PHAs in procedures for use of HMIS and will monitor utilization
3.2g) Develop process for identifying and assisting consumers in updating their contact information on Public Housing Authorities waiting list so they can be contacted when units are available |  |  |  | Include a question regarding waiting list status in the intake process. Help in updating contact information so they remain in an Active Status on the PHAs’ Waiting Lists.
Strategy 3.3) Promote increasing the number of fully accessible and universally designed units for physically challenged persons in new mixed development projects.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.3a) Meet with developers to discuss the need and development of new accessible and universally designed units and present incentives available to them such as Project Based Vouchers. | Housing Committee |  | Increase number of available units
3.3b) Promote new development with more accessible set-aside units for extremely low- and low-income persons. | Housing Committee |  |  | Encourage developers to include a preference for homeless persons with extremely low- and low-income households. Also encourage developers to have a Set A Side for extremely low- and low-income households.
Strategy 3.4) Expand Rapid Re-Housing (RRH).
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.4a) Continuum of Care (CoC) to prioritize Rapid Re-Housing as a priority for allocation and re-allocation of projects in HUD CoC Application | Housing Committee, CACH Board |  | Funds Reallocated | Funds have been reallocated
3.4b) Assist RRH participants to complete applications for subsidized permanent housing or develop income sources to apply and maintain unsubsidized permanent housing.
3.4c) Review reallocating HUD CoC funding currently designated for transitional housing to RRH in future funding requests. | Housing, and Coordinating Committees |  | Completed | Completed
Strategy 3.5) Identify existing and emerging sources for homeless rental assistance such as PHARE, HOMEE4GOOD, State and County Housing Trust funds, etc.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.5a) Generate an inventory of existing grant/funding resources that provide funding for rental subsidies for services providers. Monitor new funding/grant announcements and notify services providers availability | Housing Committee |  | Inventory list completed and made available. | CACH currently distributes funding opportunities to service networks.
3.5b)) Research and apply for Requests for Proposals for rental assistance | Housing Committee, Service Providers |  |  | Ongoing. Secured (94) 811 Vouchers and 15 Mainstream Vouchers in 2020. Secured and additional Emergency Vouchers in 2021.
STRATEGY 3.6: Expand Permanent Supportive Housing (PSH) for those needing ongoing service enriched housing e.g., chronically homeless, disabled, etc.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
Apply for PHFA Housing Assistance Program Grants such as 811 and Mainstream Vouchers | Housing, Service Delivery Committees, HRA Staff, PHAs | Ongoing | Increase number of available vouchers. | Explored availability of funding from Continuum of Care Grant. Secured (41) 811 Vouchers and 15 Mainstream Vouchers in 2020. Secured and additional Emergency Vouchers in 2021.Continue to respond to RFPs.
STRATEGY 3.7: Explore funding to provide community-based case management to assist homeless participants who may not be part of a target or disabled population in applying and retaining permanent housing
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.7a) Identify funding for case management services to non-targeted populations consumers | Housing and Service Delivery Committee |  | Consumers receiving Street Outreach Services are being assisted in obtaining housing | Funding secured for Street Outreach to homeless population to assist in obtaining housing and services. Health care providers also providing Street Outreach. New funding will be needed when COVID funds expended. Center for Peace and Justice and Fair Housing providing services to assist in housing stability
STRATEGY 3.8: Develop a collaborative relationship with the Housing Providers Community (Public HHAs, developers and private landlords) to promote housing for homeless populations with emphasize on special needs/vulnerable population
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.8a) Create and maintain a master landlord referral list which is available to CACH homeless providers | Housing Committee
3.8b) Educate landlords to the supportive services provided to consumers to support their successful residency and engage landlords in trying to reduce barriers to tenancy for individuals with a criminal background. | Housing Committee
3.8c) Encourage the participation of at least one representative from the Capital Area Landlord Association in the CACH committee structure. | Housing Committee |  | Completed | Member of Capital Area Property Owners Assoc attends meetings regularly.
3.8d) Regularly engage the local landlord association, CARPOA, to continue to implement and monitor the utilization of the Landlord Protocol that provides a community supportive services response to tenants not complying with their lease and facing possible eviction. | Housing Committee |  |  | Plan for future centralized phone number by Dauphin County Human Services (717-780-6288) for landlords to contact for tenants with behavioral health issues which are negatively affecting their tenancy and may cause possible eviction action.
STRATEGY 3.9: Expand dedicated supportive housing for unaccompanied homeless children and youth
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.9a) Encourage relevant youth service and/or rapid rehousing agencies e.g., Valley Youth House, CCU, etc., to develop housing options through Dauphin County Children and Youth | Valley Youth and Thrive. Unaccompanied Youth Subcommittee |  | Increase housing option available for youth by 10%. | Unaccompanied Youth Subcommittee is conducting a survey to access the need for housing needs for the population. To be completed in March 2022
3.9b) Re-categorize existing transitional housing to serve youth ages 18-24 with culturally competent supportive services especially for those aging out of foster care and LGBTQ. | Housing and Service Delivery Committees, Valley Youth |  |  | Thrive housed 10 youths- referred by Valley Youth. 15 youth housed through Harrisburg Housing Authority transition from Foster Care Program .
3.9c) Homeless Youth Sub-Committee of the Service Delivery Committee will assist and encourage capable stakeholder agencies where feasible to apply for relevant target population housing e.g., HHS-ACF-Runaway Homeless Youth (RHY) Basic Center (shelter), TH and outreach. | Housing and Service Delivery Committees, Valley Youth
3.9d) Develop new housing options for unaccompanied adults, ages 18-24 years of age. | Valley Youth, Thrive and Housing Committee |  | Increase housing option available for youth by 10%. | Children and Youth contracted with Valley Youth and Scholars/Thrive for the provision of housing for 10 youths. Harrisburg Housing has a grant for 15 Family Unification Vouchers for youth aging out of foster care.
3.9e) Form an Unaccompanied Youth Task Force to prepare a report for the Housing Committee that identifies housing needs for this age group and to inventory exiting resources. | Tabitha Kramer, Unaccompanied Youth Task Force |  | Submit a report to the Housing Committee with recommendations regarding the housing needs for Unaccompanied Youth. | Committee is reviewing current definitions of homelessness for youth, potential funding resources, and exploring them need for shelter. Also exploring the need for a permanent committee to focus on the needs of Unaccompanied Homeless Youth as part of the CACH's organizational planning process.
Strategy 3.10) Reduce family homelessness through creating new and effectively using existing housing options.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CURATIVE PROGRESS
3.10a) Maintain homeless family priority for housing in CoC "Written Standards." | Housing Committee |  | Complete review with recommendations | Review Standards to update. Review CES Priority Ranking pertaining to families
3.10b) Expand and make efficient the Family Unification Program (FUP) housing vouchers. | Housing Committee |  | Full utilization of the FUP Program and exploration of expansion | Review current use and structure. Review current MOU and contracts
3.10B.i) Move FUP recipients whose children are no longer minors into mainstream Housing Choice Section 8 Vouchers. | Housing Committee |  |  | Review feasibility. Explore if process is available
3.10c) Expand options for housing large homeless families, such as prioritizing Rapid Rehousing services for scattered site single family housing with 5+ bedrooms and developing relevant landlord networks to know where such units exist | Housing Committee |  |  | Review feasibility
STRATEGY 3.11: Develop temporary housing and shelter to meet the needs for unsheltered and vulnerable/at risk persons/households with special needs
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.11a) Explore the feasibility of developing Low Demand Shelters for men and and women | Housing Committee |  |  | Stakeholders identified. In process of scheduling meeting with potential service providers, stakeholders, and funding entities
3.11b) Explore increasing the shelter capacity for Victims of Domestic Violence | Housing Committee
3.11c) Explore the need for the development of a Safe Haven for Victims of Human Trafficking | Housing Committee
3.11d) Explore the development of shelter care for households with fathers with children | Housing Committee
STRATEGY 3.12) Explore Medicaid as a funding source for case management for permanent supportive housing.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.13a) Support implementation of Community Health Choices Dual Eligible Case Management Services | Housing, and Serv Delivery Committees
STRATEGY 3.13) Explore creating a "Landlord Incentive Fund" for rental related expenses including required expenses not covered by some rental subsidy programs.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.14a) Determine the scenarios for this fund e.g., security and utility deposits not covered by a rental program, first and last month’s rent for those with bad rental history or credit, or damages that exceed the security deposit. | Housing and Planning and Resource Development Committees |  | Program Implemented | Funding secured. Boucher completed. Training planned for service providers
3.14b) Determine trustee ownership of this Fund and operating rules and parameters for payment and repayment back into the fund pool. | Housing and Planning and Resource Development Committees |  | Completed | Housing Authority of the County of Dauphin will provide administrative support for the program and maintain financial records.
3.14c) Identify untapped or allocable sources for this Fund | Housing and Planning and Resource Development Committees
STRATEGY 3.14) Explore the expansion of representative payee options specific to rent payment.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.15a)Conduct a feasibility study | Housing and Prevention Committees |  |  | Collaborate with the Prevention Committee. Explore as a resource, Maranatha of Carlisle for expansion of their existing payee services
STRATEGY 3.15) Preserve existing affordable housing projects/developments for low income households
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.16a) Convene a task force of county housing development corporations, housing authorities, redevelopment authorities, local government entities to identify properties at risk and to develop strategies to preserve the properties (units) as affordable for low-income households | Housing Committee and Affordable Housing Preservation Task Force |  |  | Bryan Davis has volunteered to assist in convening an initial meeting. Mike Weisberg has prepared an analysis identifying properties and pending expiration dates
STRATEGY 3.16) Mobilize the community and public officials to support the development of new affordable housing options for extremely low- and low-income households
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
Mobilize the community through advocacy initiatives, education, formation of partnerships and collaborations to increase the availability of affordable housing.
3.17a).Mobilize the community through advocacy initiatives, education, formation of partnerships and collaborations to increase the availability of affordable housing. | Housing Committee |  | Increase the production of affordable housing | CACH’s housing needs analysis has been completed. Draft of housing needs assessment for the CACH population is completed. Testimony has been submitted regarding the housing needs for inclusion in the Dauphin County Consolidated Plan. City and County Officials have received projects under development that CACH has endorsed for potential funding for the Home-ARP Program
STRATEGY 3.17) Explore the feasibility for development of Respite Care for homeless persons discharged from the hospital and needing supportive housing for their recovery
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.18a) Conduct a needs assessment and form collaborative relationships with community partners to explore the potential development of respite care housing | Housing Committee |  |  | Contact made with UPMC, UPMC Health Insurance and Penn State Health
STRATEGY 3.18) Development and expansion of transitional housing programs.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | CUMULATIVE PROGRESS
3.18a) Development of a Tiny Home Village for veterans | Housing Committee & Veteran Outreach of PA |  |  | Site preparation in progress. Seeking Home-ARP funding. Endorsed by Housing Committee
3.18b) expand capacity of Transitional Housing for young adults | Housing Committee & Thrive |  |  | Seeking Home-arp Funding. Endorsed by Housing Committee

## Goal 4 SERVICE DELIVERY
OBJECTIVE 4: Access to and Availability of Supportive Services – To increase access to timely, appropriate, affordable and easily accessible supportive services which can help end homelessness and prevent its recurrence |  |  |  |  | RETURN TO INDEX
STRATEGY 4.1 Continue to have representation from the Drop-in Center (Downtown Daily Bread & Shalom House) on the Service Delivery committee to provide additional resources.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s)- NEXT STEPS | Cumulative Progress
4.1.a) Continue to share resources and training opportunities with within the Service Delivery committee meetings. | Service Delivery | Ongoing | Identify resources offered by community agencies. | To date the committee does not have any representation from Our Daily bread attending meetings. We do not currently have a housing case manager meeting.
4.1b) Provide information to the CACH point of contact regarding upcoming traings and resources for the CACH website. | CACH Members, CACH Staff as Point Person, Public Education & Information |  |  | No progress to report. This goal should be a goal for all CACH committees and CACH staff to funnel information down to the staff or team that updates the website.
STRATEGY 4.2: Seek representation from Mental Health, Medical Professionals, and Drug & Alcohol in efforts to strengthen communication and partnerships to assure prompt access to the services their systems provide.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s)- NEXT STEPS | Cumulative Progress
4.2.a) Ensure seamless communication and coordination with and between SOAR, CMU outreach, PATH outreach, Crisis Outreach and Shelter + Care and the continuum so that these services and referrals do not operate in silos. | Service Delivery | 2022-10-22 | To restart these discussion in Service Delivery Meetings. Recruit more participants. | A small group was established to discuss drop-in needs. The meetings included Frank Magel and Rose Schultz (Dauphin County MH) and Leila Simmons (CMU). This small group looked what MH services are available and how we can make them accessible in the comminuty.
4.2.b) Coordinate with mobile health outreach to reach more unsheltered persons. | Service Delivery, Prevention | 2022-10-22 | Develop a list of providers that offer mobile health services. Reach out to invite to Service Delivery. | No progress to report.
4.2.c) Explore bringing HHS Health Care for the Homeless Centers and services to the continuum. | Serv Delivery, Long Range Plan |  |  | No progress to report. What is HHS Health Care?
4.2.d) Work with key stake holders (public, state, private, and faith based) to adopt practices and policies which can increase access for and in some cases prioritize people experiencing homelessness for MH and D&A services. | Serv Delivery, Public Education, Coordinated Entry
OBJECTIVE 4.3: Develop training opportunities for case managers and also community volunteers to facilitate a better understanding of the underlying causes of homelessness, improve referrals, strengthen case management practices and maximize coordination of available services (public, private, faith based).
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s)- NEXT STEPS | Cumulative Progress
4.3a) New Goal- Develop a Case Management Resoucre Guide that includes a Tool Kit. This will offer partner agencies with best pratices and tools for their case management team to use. This will also streamline how case management is being done across agency. | Serv Delivery, Public Education & Information |  | Identify Best Practices Recruit a small Case Management Group
4.3b) Develop 2 annual half day trainings for case managers and front line staff to attend. | Service Delivery | 2022-10-22 | Include elements in training series on needs of unique populations including formerly incarcerated individuals, inidividuals with MH/ID and substance abuse issues, unaccompanied youth, and LGBTQ individuals. | Leah Payne from Help Ministries is currently working with a small group to pull off a Awareness Symposium in the fall. The symposium will bring awareness of services and the needs for the homeess popultaion.
4.3c) Create a case managers group that can meet every other month to review cases and dicuss best practices. | Service Delivery | 2022-10-23 | SOAR & Mainstream Programs & Benefits
STRATEGY 4.4: Improve access to mainstream programs and services to reduce people’s vulnerability to homelessness and to reduce time spent in the homeless system.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s)- NEXT STEPS | Cumulative Progress
4.4a) Advocate for expedited application and enrollment processes to mainstream programs for people identified as experiencing homelessness. | Service Delivery Public Education & Information |  | Identify programs and program contacts that we need to expedite applications or enrollment . Invite them to the service delivery committee meetings to dicuss ways to improve enrollment for homeless individuals. | No progress to report.
4.4.b) Expand SOAR to include disabilities other than mental health and intellectual development. | Service Delivery |  |  | No progress to report.
STRATEGY 4.5 Expand use of HMIS to measure current and yet to be identified supportive services outcomes.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
4.5a) CACH Staff will provide HMIS Data to discuss during committee meetings | Service Delivery, Data | Ongoing

## GOAL 5 PUBLIIC INFORMATION &
OBJECTIVE 5: Public Awareness and Education- To increase the community’s awareness of homelessness upon individuals and families and to generate their support and participation in the unified efforts of the coalition to prevent and end homelessness in our community.
STRATEGY 5.1: Inform the community of the need for public, foundation and private funding to sustain and expand the services needed to provide services and housing for homeless persons.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
5.1.a) Prepare quality, factual and motivational materials about homelessness in our community for specific audiences: the general public, government officials, private non-profit, faith and community based organizations, to garner their support funding initiatives and legislative initiatives to that benefit homeless households. | Public Information and Education
5.1.b) Develop an informational guide to educate the community about CACH and its partners’ plan to end homelessness and ways they can lend their support and participate as volunteers. | Public Information and Education
5.1.c) Maintain an up-to-date CACH website to inform and educate the community about the needs of homeless households. | Public Information and Education
5.1.d) Distribute an Annual Report to the community | Public Information and Education
5.1.f) Develop a media marketing plan | Public Information and Education
STRATEGY 5.2: Develop a marketing plan with a unified message that will generate support from the community and stakeholders whose participation/partnership will benefit the organization.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
5.2.a) Distribute an Annual Report to the community through social and mainstream media describing the Coalition's impact on preventing and ending homelessness. | Public Information and Education
5.2.b) Develop a marketing plan to inform students/faculty from higher education institutions about homelessness in our community to promote recruitment of student interns and volunteers for CACH's programs and services. | Public Information and Education
5.2.c) Develop a media marketing plan to describe the extent of homelessness in our community and the impact of CACH's services/program in preventing homelessness, making it brief should it occur and making it non reoccurring.. | Public Information and Education
STRATEGY 5.3: Promote support for governmental policies, procedures and funding that will benefit homeless individuals and families.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
5.3.a) Conduct and promote an annual event with for CACH's members, partners, and clients to meet with public/private officials to promote services and programs benefitting the homeless population | Public Information and Education
5.3.b) Educate CACH partners about new or pending legislation that will affect homeless clients. | Public Information and Education
5.3.c) Develop the a unified marketing plan with member agencies that promotes the services and programs of CACH for distribution to public officials and the community. | Public Information and Education
STRATEGY 5.4: Engage and partner with the faith based community and social service providers to developed services and programs that make a social impact on homelessness
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
5.4a) Partner with service providers and the faith based community to develop programs to prevent homelessness and to provide of services to households experiencing it. | Public Information and Education
RETURN TO INDEX

## GOAL 6 PREVENTION
OBJECTIVE 6: Prevention- To develop strategies to reduce the occurrence of homelessness in Dauphin County. |  |  |  |  | RETURN TO INDEX
STRATEGY 6.1: Develop unified and coordinated prevention activities utilizing all public, private and faith-based organizations serving homeless individuals and families.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
6.1.a) Encourage the use of the coordinated entry system by all public, private and faith-based organizations in encountering people at risk of homelessness. | Prevention and Service Delivery Committees
STRATEGY 6.2: Explore developing interventions to maintain all individuals and families in their home. using resources such as Emergency Solutions Grant - Homeless Prevention (ESG-HP) program.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
6.2.a) Research models for developing programs to prevent households from entering the homeless services system. | Prevention Committee
STRATEGY 6.3: Create and implement comprehensive client centered discharge planning. processes/procedures with services systems/institutions (foster care, mental health facilities jails prisons) for individuals at-risk of becoming homeless.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
6.3a) Promote discharge planning agreements with community service systems/ institutions (such as jail, prisons, foster care, hospitals, behavioral health facilities) on an annual basis to ensure appropriate permanent housing for individual at risk of homelessness. | Prevention Committee
STRATEGY 6.4: Promote access and utilization of health care services and medical home for those who are at risk of homelessness due to medical issues or medical costs.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
6.4a) Promote Health Insurance enrollment and connection to Primary Care Providers for those at risk of homelessness. | Prevention, Public Education and Information Committees
6.4b) Promote information and education regarding appropriate use and access to healthcare services for those at risk of homelessness. | Prevention, Public Education and Information
STRATEGY 6.5: Promote the use of life skills programs to assist at-risk clients to prepare for employment
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
6.5.a) Identify and support agencies and organizations that provide literacy, financial management, and employment training and supported employment (Ticket to Work, Center for Employment, Education, and Entrepreneurship Development, Career Link, OVR, Goodwill and The Program) | Prevention Committee
STRATEGY 6.6: Increase and promote the use of resources for existing rental and utility assistance programs such the County Assistance Office (CAO), Department of Human Services Rental Assistance Program (RAP) and Dauphin County’s DHS allocation of Homeless Assistance Program (HAP) rental assistance.
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
6.6.a) Provide on-going information and education to community case managers and CACH partners. | Prevention Committee
STRATEGY 6.7: Impalement an Eviction Mediation Program to reduce the number of evictions from the court system
Action Step Description | Responsible Entities | Target Date | Measurable Outcome(s) | Cumulative Progress
6.7a)Partner with community agencies to develop a Eviction Mediation Program with case management and legal services. | Central Penn Legal Services and the Neighborhood Dispute Center |  |  | Program initiated, but has limited funding for 6 months
6.7b) Obtain long term funding for the Eviction Mediation Program | Planning and Resource Development Committee, CACH Board
6.7c) Advocate for the required utilization of Eviction Mediation in the court for all eviction filings to reduce the rate of evictions | Prevention and Public Information and Education Committees
RETURN TO INDEX

## BP EXPECTED OUTCOMES
RETURN TO INDEX